## Sheet1
Sr.No | Defect ID | Defect Title | Description | Steps to Reproduce | Expected Result | Actual Result | Level | Severity (Level of impact: | Priority (Business urgency: | Detected By | Detected On | Environment | Project/Model | Status | Assigned To | Retested By | Retested On | Notes | Attachment/Link
Serial num. | (Unique ID for the defect) | (Short title of the defect) | (Detailed explanation about defect) | (Steps to reproduce the issue) | (Expected Behavior) | (Atual Behavior) | (L0,L1,L2,L3) | Blocker, Critical, Major, Minor) | High, Medium, Low) | (tester name who found the defect) | (Date the defect was detected) | (Dev,Live,UAT) | (Name of Model) | (New, Open, In Progress, Fixed, Closed) | (Developer Name) | (tester name who performed retesting) | (Date when the retesting done) | (any additional observations) | (Screenshots, logs, or links)
1 | 001 | Historical data index filter not working | When we applying filter on index date and index value; it is not filtering the data as per the applied filter | 1.Login to Drm --drm.samcomf.com 2.Scroll down and click on Historical index data. 3.apply filrer of index value or index date 4.Click on Submit | Filter must be working for field index data and index value | No data available in table | L2 | Major | Medium | Satish Netke | 24/06/2025 | Live | DRM Website | Open | Tanuj |  |  |  | Refer to this link:- https://sam-co.atlassian.net/browse/SMF-1451
2 | 002 | Start Date field is missing | For Perpetual frequency in start date field date not displayed it directly displayed month. | 1.Login to partner --> https://dev-partners.samcomf.com/investoraccountlist 2.Click on initiate transaction 3.select folio and click on Submit. 4.Choose Scheme(flexi) 5.Select Investment type SIP 6.Enter Amount 7.Select Frequency(Weekly) 8.Select Day 9.Select Tenure - Perpetual 9.Select Start Date | Start Date should be there. | Start date field not displayed it directly displayed month. | L2 | Major | Medium | Satish Netke | 2025-03-07 | Dev | Partner(distributor flow) | Fixed | Mannu | Satish Netke | 2025-04-07 | NA
3 | 003 | Validation Error | Validation not working for Select Day. | 1.Login to partner --> https://dev-partners.samcomf.com/investoraccountlist 2.Click on initiate transaction 3.select folio and click on Submit. 4.Choose Scheme(flexi) 5.Select Investment type SIP 6.Enter Amount 7.Select Frequency(Weekly) 8.Select Tenure - Date Wise 9.Select Start Date and End Date 10.Click on Submit | Validation shold be there for Select Day field | Navigate to Review page | L2 | Major | Medium | Satish Netke | 2025-03-07 | Dev | Partner(distributor flow) | Fixed | Mannu Rajak | Satish Netke | 2025-04-07 | NA
4 | 004 | Maximum number of installment issue | Maximum no.of installment exceeds the limit. | 1.Login to partner --> https://dev-partners.samcomf.com/investoraccountlist 2.Click on initiate transaction 3.select folio and click on Submit. 4.Choose Scheme(flexi) 5.Select Investment type SIP 6.Enter Amount 7.Select Frequency -Weekly(similar for Half Yearly and Daily) 8.Select Day 9.Select Tenure - Number of Installment. 9.Enter no. of installment for weekly(more then 2085) 10.Click on Submit | Maximum no.of installment for weekly should be 2085, Daily - 14592, Half Yearly - 80 | It Maximum no.of installment limit and Navigate to Review page | L2 | Major | Medium | Fahim Shaikh | 2025-04-07 |  | Partner(distributor flow) | Open | Mannu Rajak | Fahim Shaikh | 2025-04-07 | NA